## On Prem Migration Plan
Task # | Task Name | Dependency/ Comments | Owner | Planned Date | Status
1 | Provision access to Bitbucket Production | access to Karthik and Debasmita | Srikanth |  | Complete
2 | Provision access to Bamboo Production | access to Karthik and Debasmita | Srikanth |  | Complete
3 | Create Project in Bamboo | project name DAIMLER_ITS_CRM and provide admin access to Karthik | Srikanth |  | Complete
4 | Create Project in Bitbucket | project name DAIMLER_ITS_CRM and provide admin access to Karthik | Srikanth |  | Complete
5 | Communicate to Team Members | Communicate to team members about Migration | Karthik | 2018-04-16
6 | Bit Bucket Repositories Import | Sample repository import | Karthik |  | Complete
7 | Create Bamboo Jobs for Major/ MR and Kernel | Validate few jobs | Karthik |  | Complete
6 | Bit Bucket Repositories Import | Delete previous repository and re import | Karthik | 2018-04-20
8 | Developers Validation |  | Infosys Dev, NTT Dev | 2018-04-20
9 | Creation of Bitbucker users for all developers | list to be provided by Karthik | Srikanth | 2018-04-20
10 | Creation of Bamboo Access | 1 for Infy Dev and 1 for NTT Dev | Srikanth | 2018-04-20
11 | Final communication post Migration | Instuctions to be passed to Infy/ NTT Dev informing them to --> start using On premise Bitbucket and validate the CI/ Test jobs in Bamboo | Karthik | 2018-04-21
12 | Running Stage Job | Stage job to be run in jenkins to deploy in stage/developer pro sandbox and create tag for production deployment. Bamboo stage job will be run on top of that to check if it is working propery. | Karthik | 2018-04-23
13 | Code checkin by developers | Check in the modified code in Bitbucket cloud and on premise both from 22nd to 26th April ( for fallback plan) | Karthik
14 | Running Production Job | Production job will be executed from Bamboo for 26th Major release | Karthik | 2018-04-26

## On Prem Migration Testing
S.No. | Component Type | Component Name | Owner | Status
1 | Apex Class/ VF Page | AddressSearchValidation | Sanjay/ Prabhat | Done
2 | Apex Class | SendtoAutoline | Pavan | Done
3 | Apex Class/ VF Page | CreateRetailCopy | Sanjay/Prabhat | Done
4 | Object | Token related changes by creating a new button (DM Request) | Prabhat | Done
5 | Flows | Create new Flow | Prabhat/Karthik | Done
6 | Process Builder | Change an existing process builder. | Prabhat | Done
7 | Workflows | Workflow related changes. | Pavan/ Karthik | Done
8 | Test Class Execution | Test class execution at last. | Karthik/ Pavan | Done
9 | Profiles | Profile | Sanjay | Done
10 | General | Environment mappings for workflows and default dashboard user | Prabhat/Karthik | Done
11 | General | Retrieve feature test | Karthik/ Pavan | Done
12 | General | Checking the history | Karthik/ Pavan | Done
13 | Object | Move a full object account, lead or case or campaign. | Pavan/ Prabhata/ Sanjay | Done
14 | General | Compare the size of repository | Pavan/ Karthik | Done
15 | General | Merge validation till ASIA-UAT | All | Done
16 | Object | Kernel Sandbox and related changes | Sanjay/ Prabhat | Done
17 | Destructive | Pre/ Post Destructive | Karthik/ Pavan | Done